## GSpread
GSpread
Category: | Distributed Amount Projections
Family: | Time Spread
Arguments: | Time, Base, Start, Total, [CompletionDate], [CurveModel], [Shape], [DayCount], [Periods], [ProjMode]
Meaning: | General Spread Function
Description:
|  | Base | Start | Finish | Total | DayCount | Periods
|  | 6 | 2001-07-01 | 2004-01-01 | 1000 | Omitted | Omitted
As an Accruals Function: |  | 2001-01-01 | 2001-07-01 | 2002-01-01 | 2002-07-01 | 2003-01-01 | 2003-07-01 | 2004-01-01 | Total
Shape
0.98 |  | 0 | 95.4915 | 250 | 309.017 | 250 | 95.4915 | 0 | 1000
0.78 |  | 0 | 147.7458 | 225 | 254.5085 | 225 | 147.7458 | 0 | 1000
-99.01 |  | 0 | 34.3964 | 110.2376 | 204.8833 | 304.4748 | 346.0079 | 0 | 1000
100 |  | 0 | 1000 | 0 | 0 | 0 | 0 | 0 | 1000 | ok
0 |  | 0 | 200 | 200 | 200 | 200 | 200 | 0 | 1000 | ok
100 |  | 0 | 1000 | 0 | 0 | 0 | 0 | 0 | 1000 | ok
-100 |  | 0 | 0 | 0 | 0 | 0 | 0 | 1000 | 1000 | ok
50.5 |  | 0 | 438.4634 | 214.4782 | 152.5947 | 111.9272 | 82.5366 | 0 | 1000 | ok
0.5 |  | 0 | 169.2622 | 214.7059 | 232.0638 | 214.7059 | 169.2622 | 0 | 1000 | ok
Some examples:
100.00 All the cost on the start date
-100.00 All the cost on the finish date
0.00 The cost is evenly spread (like the UniSpread function) between the start date and finish date.
0.50 The cost is spread symetrically on an S-curve, with a moderate degree of peak.
50.50 The cost is spread an S-curve, skewed toward the start date with a moderate degree of peak
0.90 The cost is highly peaked and will occur midway between the start and finish date.
0.99 The cost will occur instantaneously at the midpoint between the start and finish dates.
Formulas:
Finish = _XLL.DPY([Start],2.5)
Finish = _XLL.DPM([Start],E12)
Start = _XLL.DPM([Base],E12)
Total = _XLL.DPM([Finish],E12)
DayCount = _XLL.DPM([Total],E12)
Periods = _XLL.DPM([DayCount],E12)